## Planning and Execution
Task #1 | Priority # | Task Name | Owner | Start Date | End Date | Status/Done% | Issues | Comment | Owner
1 | 1 | Being familiar with Python | David | WW01 | WW02 | DONE |  |  | David
2 | 1 | Being familiar with Python | Linyi | WW01 | WW02 | DONE |  |  | Linyi
3 | 1 | Being familiar with Python | Ting | WW01 | WW02 | DONE |  |  | Ting
4 | 1 | Being familiar with Python | Xiaoqiao | WW01 | WW02 | DONE |  |  | Xiaoqiao
5 | 2 | Understanding basics of Tkinter | David | WW01 | WW02 | DONE |  |  | Ataur
6 | 2 | Understanding basics of Tkinter | Linyi | WW01 | WW02 | DONE
7 | 2 | Understanding basics of Tkinter | Ting | WW01 | WW02 | DONE
8 | 2 | Understanding basics of Tkinter | Xiaoqiao | WW01 | WW02 | DONE
9 | 3 | Getting the QOR report in GUI | Linyi | WW01 | WW02 | DONE |  | Spec is on the QOR Worksheet. Linyi you have done it almost; so, I put the dates accordingly.
10 | 4 | Comparing 2 QOR reports in GUI | Linyi | WW03 | WW03 | DONE |  | Spec is on the QOR Worksheet
11 | 4 | Sorting/filtering a path's attributes: GUI in Table/Histogram Format | David | WW03 | WW03 |  |  | Spec is on Single_Path_GUI Worksheet
12 | 4 | Finding the path details report from QOR's WNS | Ting | WW03 | WW03 |  |  | Spec is on QOR_Path_Details Worksheet
13 | 4 | Report the number each cell appears in a file and the associated timing margin | Xiaoqiao | WW03 | WW03 |  |  | Spec is on Report_Analaysis Worksheet
14 | 5 | Comparing 3 or more QOR reports in GUI | Linyi | WW04 | WW04 | DONE |  | Spec is on the QOR Worksheet
15 | 6 | Difference of 2 paths with same start and end points from 2 different files | Ting | WW09 | WW10 |  |  | Spec is on Diff_2_Paths Worksheet
16 | 6 | Bottleneck report: Sorted list of cells/nets/slopes that contribute most on total -ve slack | David | WW09 | WW10 |  |  | Spec is on Bottleneck Worksheet
19 | 6 | MCMM reporting: Create a GUI view of 1 report and then show same path in other reports | Linyi | WW09 | WW10 |  |  | Spec is on MCMM_rpt Worksheet
20 |  |  | Xiaoqiao
21
Linyi/Xiaoqiao

## MCMM_rpt
Inputs:
There will be more than 1 input files with timing reports.
MCMM stands for Multi-Corner Multi-Mode
Outputs:
Have a GUI version of each of the timing reports
| 1 GUI per file. |  |  |  | 1st section
1 row per path
| For each GUI, the paths can be sorted by their start point, end point, timing slack, clock groups |  |  | 3rd section
2nd section
| The GUI will have 3sections: please see the table diagram on the left. |  |  |  | Detailed of the path chosen from 1st section will be seen here
1st section will have only the start point, end point, timing slack and clock group; means 1 row for 1 path.
2nd section will have the path details for the path chosen from the 1st section.
3rd section will give the option to search start, end, etc. in the 1st section; paths can be grep or excluded (mean we can find the path needed, or exclude the paths we don’t want to see.
Based on the 3rd sections search, 1st section will change (meaning less paths or rows to show up).
Starting from 1st file and an user chosen timing path (based on start point, end point or start/end point pairs), find the same path in other files.
Clicking on the user chosen path in 1 GUI will highlight or show up paths matching either start or end or start/end points from the path in the 1st file in other GUI or GUIs.
The user may be given option to chose in which files to search the paths from 1st file.
A GUI to GUI interaction needs to happen here.

## Bottleneck
Inputs:
A file with timing reports
Outputs:
Output of this file is extended version of Report_analysis task
Here objective is to find out all attributes of design that is bottleneck to the performance or slack of timing paths.
Based on the timing report file, find out:
|  | A) | Sorted list of cells with their total delay contribution to total -ve slack ==> this part is same as Report_analysis
|  | B) | Extend the same now with cells with highest slopes at their outputs and contributing most to the total -ve slack.
|  | C) | Extend the same now with cells with highest caps and contributing most to the total -ve slack.
|  | D) | Similarly, for nets now (instead of cells).
|  | E) | For all the above (A to D), please have a histogram to show top 10 or 20 (user defined) cells for their total contribution to delays
For all the above (A to E), please have separate GUIs to pop up.

## Report_analysis
Input file is:
/u/ataur/CAPSTONE_GUI_2018/scripts/QORs_Detailed_Timing_Report
Outputs:
Find the number of times each cell appears in that report
Example: This cell fifomem/U24/A2 appears only once.
Show the cells such way that they can be sorted by their names and how many times they appeared
Sort the cells based on how much they contributed in the negative paths.
Have the option to show only the cells that are associated with paths that have only negative (-ve) slack or a slack limit given by user:
Example: This cell rptr_empty/U10 appeared in 2 paths with -ve slack and the total -ve slack for those 2 paths are: -0.106 (-066 - 0.040)
Example: This cell rptr_empty/U10 appeared in 2 paths that have -ve (negative) slack and the total delay from that cell is 0.026 + 0.013 or 0.039 ns
The GUI, will show the cell names, their delays in -ve paths and the total -ve slack in all paths the cells appear and how many times the cells appeared.

## Diff_2_Paths
Inputs:
2 files with timing reports
A start point
An end point
Outputs:
Find the path with a given start point and end point in 1st file
Find another path with the same start point and end point in 2nd file
Find the superset of all the cells and nets between the 2 paths from above.
For each of the cells and nets in that superset, list the same info as in 1st file which are delays, slopes, cap, etc.; if no info, keep the entries empty
In each row of cells or nets, list the similar values from delays, slopes, cap, etc.
Also, add the difference between similar values from 1st report to 2nd report in the same row
Output format shown for delay values; please add similar for cap, slopes, etc. as seen in each of the files:
| Column1 | Column2 | Column3 | Column4
| Cell or net name | Delay from 1st report | Delay from 2nd report | Diff_delay

## QOR
GUI to compare QOR reports and also for analysis of Single GUI
There are 3 QOR reports now in this area which are named as with small changes among them for testing purpose:
Area: /u/ataur/CAPSTONE_GUI_2018/scripts
QOR_Report_File
QOR_Report_File_2
QOR_Report_File_3
For more QOR reports, please create similar files.
The GUIs would be:
1) GUI: For single QOR report
Sort based on Critical Path Slack
Sort based on Path Group
Sort based on Clk Period
Sort based on Levels of Logic
Effectively allow user to sort based on every line of attributes (ex: Path Slack)
Show the path group's information based on user given search criteria which could be exact or regular expression: For example show only those groups that have "PUTS" in their name.
2) GUI: For 2 QOR reports
The same as single QOR GUI above, however, have 2 columns or rows adjacent to each other for the comparison of same items between 2 QOR reports
2) GUI: For 3 or more QOR reports
The same as single QOR GUI above, however, have 3 or more columns or rows adjacent to each other for the comparison of same items among 3 or more QOR reports

## QOR_Path_Details
The objective of this GUI is to show in a pop up window, the details of the path that has the worst margin in QOR report:
QOR report file lists the path with the worst margin.
Input files:
In this area: /u/ataur/CAPSTONE_GUI_2018/scripts
QOR_Report_File
QORs_Detailed_Timing_Report
Steps:
Start from a path group and find the Critical Path Slack
Then, from the QORs_Detailed_Timing_Report file, find the Path Group and the Slack that matches with that from QOR report file.
Show that single path from Startpoint till slack
Example:
For the "Timing Path Group 'INPUTS'" ==> the pop up GUI will have the one shown on the left:
From QOR_Report_File which matches the path from QORs_Detailed_Timing_Report

## Single_Path_GUI
Inputs:
User will give Startpoint, Endpoint or Path Group which are in a file: Goal is to find the path and geneate Tables and Histograms
The input file is: /u/ataur/CAPSTONE_GUI_2018/scripts/QORs_Detailed_Timing_Report
Also, the user might just give a file with 1 single path and hence, no start/end point will be given.
Example:
User will give the following 3 inputs; or, may be only 1 of those 3 or none if the file has only 1 path:
For example
|  | Startpoint | rptr_empty/rempty_reg
|  | Endpoint | rptr_empty/rbin_reg[2]
|  | Path Group: | rclk
Outputs:
We will have GUI in both Table and Histogram format for a single path asked by user which will be in a file name given by user
Based on the user input file and other user inputs (Startpoint, etc.), find the path with worst margin and then for that path:
Sort the file based on the value in Incr column
Sort the file based on the value in Cap column
Sort the file based on the value in Trans column
For the Table format, let's keep all the contents as in the origianl file.
When a user click on say, Cap then a pop up GUI will come up with Histograms to show the same values as in the Table but, in graphical format
The Histogram would be based on the sorted values of Cap for the above example in the line above.
Please make the script generic, meaning later on there may be more columns and hence, we will need to sort based on them also.