## Planning and Execution
Task #1 | Priority # | Task Name | Owner | Start Date | End Date | Status/Done% | Issues | Comment | Onwers
1 | 1 | Being familiar with Python | David | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now | David
2 | 1 | Being familiar with Python | Linyi | WW01 | WW02 | DONE |  | Please let me know if this task is done by now | Linyi
3 | 1 | Being familiar with Python | Tina | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now | Tina
4 | 1 | Being familiar with Python | Xiaoqiao | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now | Xiaoqiao
5 | 2 | Understanding basics of Tkinter | David | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now | Ataur
6 | 2 | Understanding basics of Tkinter | Linyi | WW01 | WW02 | DONE |  | Please let me know if this task is done by now
7 | 2 | Understanding basics of Tkinter | Tina | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now
8 | 2 | Understanding basics of Tkinter | Xiaoqiao | WW01 | WW02 | DONE? |  | Please let me know if this task is done by now
9 | 3 | Getting the QOR report in GUI | Linyi | WW01 | WW02 | DONE |  | Spec is on the QOR Worksheet. Linyi you have done it almost; so, I put the dates accordingly.
10 | 4 | Comparing 2 QOR reports in GUI | Linyi | WW03 | WW03 |  |  | Spec is on the QOR Worksheet
11 | 4 | Sorting/filtering a path's attributes: GUI in Table/Histogram Format | David | WW03 | WW03 |  |  | Spec is on Single_Path_GUI Worksheet
12 | 4 | Finding the path details report from QOR's WNS | Tina | WW03 | WW03 |  |  | Spec is on QOR_Path_Details Worksheet
13 | 4 | Report the number each cell appears in a file and the associated timing margin | Xiaoqiao | WW03 | WW03 |  |  | Spec is on Report_Analaysis Worksheet
14 | 5 | Comparing 3 or more QOR reports in GUI | Linyi | WW04 | WW04 |  |  | Spec is on the QOR Worksheet
16
17
18
19
20
21
22

## QOR
GUI to compare QOR reports and also for analysis of Single GUI
There are 3 QOR reports now in this area which are named as with small changes among them for testing purpose:
Area: /u/ataur/CAPSTONE_GUI_2018/scripts
QOR_Report_File
QOR_Report_File_2
QOR_Report_File_3
For more QOR reports, please create similar files.
The GUIs would be:
1) GUI: For single QOR report
Sort based on Critical Path Slack
Sort based on Path Group
Sort based on Clk Period
Sort based on Levels of Logic
Effectively allow user to sort based on every line of attributes (ex: Path Slack)
Show the path group's information based on user given search criteria which could be exact or regular expression: For example show only those groups that have "PUTS" in their name.
2) GUI: For 2 QOR reports
The same as single QOR GUI above, however, have 2 columns or rows adjacent to each other for the comparison of same items between 2 QOR reports
2) GUI: For 3 or more QOR reports
The same as single QOR GUI above, however, have 3 or more columns or rows adjacent to each other for the comparison of same items among 3 or more QOR reports

## QOR_Path_Details
The objective of this GUI is to show in a pop up window, the details of the path that has the worst margin in QOR report:
QOR report file lists the path with the worst margin.
Input files:
In this area: /u/ataur/CAPSTONE_GUI_2018/scripts
QOR_Report_File
QORs_Detailed_Timing_Report
Steps:
Start from a path group and find the Critical Path Slack
Then, from the QORs_Detailed_Timing_Report file, find the Path Group and the Slack that matches with that from QOR report file.
Show that single path from Startpoint till slack
Example:
For the "Timing Path Group 'INPUTS'" ==> the pop up GUI will have the one shown on the left:
From QOR_Report_File which matches the path from QORs_Detailed_Timing_Report

## Single_Path_GUI
Inputs:
User will give Startpoint, Endpoint or Path Group which are in a file: Goal is to find the path and geneate Tables and Histograms
The input file is: /u/ataur/CAPSTONE_GUI_2018/scripts/QORs_Detailed_Timing_Report
Also, the user might just give a file with 1 single path and hence, no start/end point will be given.
Example:
User will give the following 3 inputs; or, may be only 1 of those 3 or none if the file has only 1 path:
For example
|  | Startpoint | rptr_empty/rempty_reg
|  | Endpoint | rptr_empty/rbin_reg[2]
|  | Path Group: | rclk
Outputs:
We will have GUI in both Table and Histogram format for a single path asked by user which will be in a file name given by user
Based on the user input file and other user inputs (Startpoint, etc.), find the path with worst margin and then for that path:
Sort the file based on the value in Incr column
Sort the file based on the value in Cap column
Sort the file based on the value in Trans column
For the Table format, let's keep all the contents as in the origianl file.
When a user click on say, Cap then a pop up GUI will come up with Histograms to show the same values as in the Table but, in graphical format
The Histogram would be based on the sorted values of Cap for the above example in the line above.
Please make the script generic, meaning later on there may be more columns and hence, we will need to sort based on them also.

## Report_analysis
Input file is:
/u/ataur/CAPSTONE_GUI_2018/scripts/QORs_Detailed_Timing_Report
Outputs:
Find the number of times each cell appears in that report
Example: This cell fifomem/U24/A2 appears only once.
Show the cells such way that they can be sorted by their names and how many times they appeared
Sort the cells based on how much they contributed in the negative paths.
Have the option to show only the cells that are associated with paths that have only negative (-ve) slack or a slack limit given by user:
Example: This cell rptr_empty/U10 appeared in 2 paths with -ve slack and the total -ve slack for those 2 paths are: -0.106 (-066 - 0.040)
Example: This cell rptr_empty/U10 appeared in 2 paths that have -ve (negative) slack and the total delay from that cell is 0.026 + 0.013 or 0.039 ns
The GUI, will show the cell names, their delays in -ve paths and the total -ve slack in all paths the cells appear and how many times the cells appeared.